## Dashboard
ULTRAS — PROJECT DASHBOARD
16-week portfolio MVP beginning 18 August 2026. Update the Task Tracker and this dashboard recalculates.
TOTAL TASKS 207 |  |  | COMPLETE 2 |  |  | OVERALL PROGRESS 1% |  | OVERDUE 0
Progress by phase | [5 empty] | Task status
Phase | Tasks | Complete | Progress | Est. Hours | State
Discovery & Scope | 17 | 2 | 11.76% | 36 | In Progress
UX & Product Design | 14 | 0 | 0% | 41.5 | Not Started
Technical Design | 15 | 0 | 0% | 47.5 | Not Started
Foundation & Data | 24 | 0 | 0% | 80.5 | Not Started
Football Core | 22 | 0 | 0% | 79 | Not Started
Accounts & Community | 38 | 0 | 0% | 151.5 | Not Started
ML & Notifications | 37 | 0 | 0% | 137 | Not Started
Release & Portfolio | 40 | 0 | 0% | 166 | Not Started
Weekly workload and completion
Week | Focus | Planned Tasks | Complete | Progress | Planned Hours |  | Current operating rule
1 | Research and definition | 17 | 2 | 11.76% | 36 |  | Complete or consciously reschedule unfinished critical P0 work before starting P1/P2 features.
2 | UX and interface design | 14 | 0 | 0% | 41.5
3 | Technical and security design | 15 | 0 | 0% | 47.5
4 | Project foundation | 12 | 0 | 0% | 36.5
5 | Football data integration | 12 | 0 | 0% | 44
6 | Football information pages | 11 | 0 | 0% | 40
7 | Live match centre | 11 | 0 | 0% | 39
8 | Authentication and personalisation | 12 | 0 | 0% | 45.5 |  | Planned completion
9 | Community platform | 12 | 0 | 0% | 48 |  | Sunday 6 December 2026 One competition • secure social MVP • explainable predictions
10 | Moderation and safety | 14 | 0 | 0% | 58
11 | ML dataset and baseline | 12 | 0 | 0% | 40
12 | Improved ML and integration | 12 | 0 | 0% | 46
13 | Notifications and official links | 13 | 0 | 0% | 51
14 | Integration and optimisation | 12 | 0 | 0% | 52 |  | CAPACITY CHECK Full scope is 739 estimated hours (46.2 per week). At 20 hours per week, reduce scope or extend the schedule.
15 | Security and release testing | 14 | 0 | 0% | 61
16 | Deployment and portfolio packaging | 14 | 0 | 0% | 53

## Task Tracker
ULTRAS — TASK TRACKER
Update Status, Progress %, Actual Hours, Evidence/Link and Notes. Dashboard and weekly summaries calculate automatically.
Task ID | Phase | Week | Category | Task | Completion Criteria | Start Date | Due Date | Priority | Status | Progress % | Est. Hours | Actual Hours | Dependency | Owner | Days Remaining | Health | Evidence / Link | Notes
W01-01 | Discovery & Scope | 1 | Project | Create the ULTRAS project repository | Repository exists with clear name, description and default branch | 2026-08-18 | 2026-08-23 | Critical | Complete | 100% | 1 | 1 |  | Finlay |  | Complete
W01-02 | Discovery & Scope | 1 | Documentation | Create README and initial folder structure | README, docs, frontend, backend and ml locations are explained | 2026-08-18 | 2026-08-23 | High | Complete | 100% | 1.5 | 1 | W01-01 | Finlay |  | Complete
W01-03 | Discovery & Scope | 1 | Product | Write the one-page project brief | Problem, audience, outcome, scope and success criteria fit on one page | 2026-08-18 | 2026-08-23 | Critical | Not Started | 0% | 2 | 0 |  | Finlay | 5 | On Track
W01-04 | Discovery & Scope | 1 | Product | Define primary and secondary users | At least three evidence-oriented user descriptions are documented | 2026-08-18 | 2026-08-23 | High | Not Started | 0% | 1.5 | 0 | W01-03 | Finlay | 5 | On Track
W01-05 | Discovery & Scope | 1 | Product | Separate P0, P1 and P2 features | Every blueprint feature is assigned a release priority | 2026-08-18 | 2026-08-23 | Critical | Not Started | 0% | 2 | 0 | W01-03 | Finlay | 5 | On Track
W01-06 | Discovery & Scope | 1 | Product | Write the explicit out-of-scope list | DMs, media uploads and real-money resale are clearly excluded from P0 | 2026-08-18 | 2026-08-23 | Critical | Not Started | 0% | 1 | 0 | W01-05 | Finlay | 5 | On Track
W01-07 | Discovery & Scope | 1 | Documentation | Create decision log and research tracker | Reusable templates exist for decisions, evidence and open questions | 2026-08-18 | 2026-08-23 | High | Not Started | 0% | 1.5 | 0 |  | Finlay | 5 | On Track
W01-08 | Discovery & Scope | 1 | Project | Create the 16-week project board | Tasks are visible by week, status, priority and dependency | 2026-08-18 | 2026-08-23 | High | Not Started | 0% | 1.5 | 0 | W01-05 | Finlay | 5 | On Track
W01-09 | Discovery & Scope | 1 | Research | Define football-data provider comparison criteria | Coverage, latency, history, players, limits, cost and licence are included | 2026-08-18 | 2026-08-23 | Critical | Not Started | 0% | 2 | 0 |  | Finlay | 5 | On Track
W01-10 | Discovery & Scope | 1 | Research | Shortlist and compare football-data providers | At least three providers are scored with evidence and URLs | 2026-08-18 | 2026-08-23 | Critical | Not Started | 0% | 4 | 0 | W01-09 | Finlay | 5 | On Track
W01-11 | Discovery & Scope | 1 | Research | Complete competitor experience audit | Live scores, feeds, discussions, alerts, safety and links are compared | 2026-08-18 | 2026-08-23 | High | Not Started | 0% | 3 | 0 |  | Finlay | 5 | On Track
W01-12 | Discovery & Scope | 1 | Research | Write supporter interview questions | Questions cover match habits, alerts, discussion, trust and safety | 2026-08-18 | 2026-08-23 | Medium | Not Started | 0% | 1.5 | 0 |  | Finlay | 5 | On Track
W01-13 | Discovery & Scope | 1 | Research | Research safety, privacy and ticket risks | Initial findings and matters requiring authoritative review are recorded | 2026-08-18 | 2026-08-23 | Critical | Not Started | 0% | 3 | 0 |  | Finlay | 5 | On Track
W01-14 | Discovery & Scope | 1 | Security | Create initial product risk register | Risk, impact, likelihood, mitigation and owner are recorded | 2026-08-18 | 2026-08-23 | Critical | Not Started | 0% | 2 | 0 | W01-13 | Finlay | 5 | On Track
W01-15 | Discovery & Scope | 1 | Documentation | Draft the Product Requirements Document | P0 requirements are testable and mapped to user value | 2026-08-18 | 2026-08-23 | Critical | Not Started | 0% | 4 | 0 | W01-05 | Finlay | 5 | On Track
W01-16 | Discovery & Scope | 1 | Product | Write P0 user stories and acceptance criteria | Every P0 journey has testable acceptance conditions | 2026-08-18 | 2026-08-23 | Critical | Not Started | 0% | 3 | 0 | W01-15 | Finlay | 5 | On Track
W01-17 | Discovery & Scope | 1 | Project | Define portfolio definition of done | Deployment, tests, docs, ML evidence and demo requirements are explicit | 2026-08-18 | 2026-08-23 | High | Not Started | 0% | 1.5 | 0 | W01-15 | Finlay | 5 | On Track
W02-01 | UX & Product Design | 2 | UX | Create the complete sitemap | Every P0 page is placed in a clear hierarchy | 2026-08-24 | 2026-08-30 | Critical | Not Started | 0% | 2 | 0 | W01-15 | Finlay | 12 | On Track
W02-02 | UX & Product Design | 2 | UX | Define main mobile and desktop navigation | Home, Matches, Explore, Notifications and Profile are covered | 2026-08-24 | 2026-08-30 | Critical | Not Started | 0% | 2 | 0 | W02-01 | Finlay | 12 | On Track
W02-03 | UX & Product Design | 2 | UX | Design registration and onboarding flow | Registration, verification, favourites and first-feed state are shown | 2026-08-24 | 2026-08-30 | High | Not Started | 0% | 2.5 | 0 | W02-01 | Finlay | 12 | On Track
W02-04 | UX & Product Design | 2 | UX | Design follow and notification flows | Team follow and granular alert preferences have success/error states | 2026-08-24 | 2026-08-30 | High | Not Started | 0% | 2 | 0 | W02-01 | Finlay | 12 | On Track
W02-05 | UX & Product Design | 2 | UX | Design match discussion and reporting flows | Posting, reporting, blocking and moderation feedback are shown | 2026-08-24 | 2026-08-30 | Critical | Not Started | 0% | 3 | 0 | W02-01 | Finlay | 12 | On Track
W02-06 | UX & Product Design | 2 | UX | Design official page claim flow | Request, evidence, review, approval and rejection states are shown | 2026-08-24 | 2026-08-30 | Medium | Not Started | 0% | 2 | 0 | W02-01 | Finlay | 12 | On Track
W02-07 | UX & Product Design | 2 | UX | Create low-fidelity Home feed wireframes | For You, Following, empty and provider-error states are included | 2026-08-24 | 2026-08-30 | Critical | Not Started | 0% | 3 | 0 | W02-02 | Finlay | 12 | On Track
W02-08 | UX & Product Design | 2 | UX | Create low-fidelity Match Centre wireframes | Upcoming, live, half-time, final and postponed states are included | 2026-08-24 | 2026-08-30 | Critical | Not Started | 0% | 4 | 0 | W02-02 | Finlay | 12 | On Track
W02-09 | UX & Product Design | 2 | UX | Create team and player page wireframes | Information and community content are visually separated | 2026-08-24 | 2026-08-30 | Critical | Not Started | 0% | 3 | 0 | W02-02 | Finlay | 12 | On Track
W02-10 | UX & Product Design | 2 | UX | Create profile, notifications and moderator wireframes | Core account and safety screens are represented | 2026-08-24 | 2026-08-30 | High | Not Started | 0% | 3 | 0 | W02-02 | Finlay | 12 | On Track
W02-11 | UX & Product Design | 2 | UI | Define ULTRAS visual design tokens | Colour, type, spacing, radius, elevation and states are documented | 2026-08-24 | 2026-08-30 | High | Not Started | 0% | 3 | 0 | W02-07 | Finlay | 12 | On Track
W02-12 | UX & Product Design | 2 | UI | Design reusable interface components | Match cards, posts, forms, tables, buttons and status states exist | 2026-08-24 | 2026-08-30 | High | Not Started | 0% | 4 | 0 | W02-11 | Finlay | 12 | On Track
W02-13 | UX & Product Design | 2 | UI | Create high-fidelity core screens | Home, match, team, player, profile and moderation screens are complete | 2026-08-24 | 2026-08-30 | Critical | Not Started | 0% | 6 | 0 | W02-08 | Finlay | 12 | On Track
W02-14 | UX & Product Design | 2 | Accessibility | Review designs for accessibility | Contrast, focus, touch targets, labels and live updates are covered | 2026-08-24 | 2026-08-30 | Critical | Not Started | 0% | 2 | 0 | W02-13 | Finlay | 12 | On Track
W03-01 | Technical Design | 3 | Data | Create the database ERD | Football, identity, social, safety, notifications and ML domains are represented | 2026-08-31 | 2026-09-06 | Critical | Not Started | 0% | 5 | 0 | W01-15 | Finlay | 19 | On Track
W03-02 | Technical Design | 3 | Data | Create data dictionary | Key fields, types, constraints, sources and retention are defined | 2026-08-31 | 2026-09-06 | High | Not Started | 0% | 4 | 0 | W03-01 | Finlay | 19 | On Track
W03-03 | Technical Design | 3 | Data | Design historical player-team membership | Transfers cannot rewrite historical appearances or line-ups | 2026-08-31 | 2026-09-06 | Critical | Not Started | 0% | 2 | 0 | W03-01 | Finlay | 19 | On Track
W03-04 | Technical Design | 3 | Privacy | Define content lifecycle and retention schedule | Match chat, posts, reports, audit and account data have states | 2026-08-31 | 2026-09-06 | Critical | Not Started | 0% | 3 | 0 | W01-13 | Finlay | 19 | On Track
W03-05 | Technical Design | 3 | Architecture | Create system architecture diagram | Frontend, API, database, jobs, provider and ML boundaries are clear | 2026-08-31 | 2026-09-06 | Critical | Not Started | 0% | 3 | 0 | W03-01 | Finlay | 19 | On Track
W03-06 | Technical Design | 3 | Architecture | Design football-data ingestion flow | Validation, mapping, idempotency, corrections and freshness are covered | 2026-08-31 | 2026-09-06 | Critical | Not Started | 0% | 3 | 0 | W03-05 | Finlay | 19 | On Track
W03-07 | Technical Design | 3 | Architecture | Design notification pipeline | Events, preferences, deduplication, retries and delivery logs are covered | 2026-08-31 | 2026-09-06 | High | Not Started | 0% | 2.5 | 0 | W03-05 | Finlay | 19 | On Track
W03-08 | Technical Design | 3 | API | Draft API specification | P0 routes include inputs, outputs, permissions, errors and limits | 2026-08-31 | 2026-09-06 | Critical | Not Started | 0% | 5 | 0 | W03-01 | Finlay | 19 | On Track
W03-09 | Technical Design | 3 | Security | Design authentication and session model | Registration, verification, recovery, cookies and sessions are specified | 2026-08-31 | 2026-09-06 | Critical | Not Started | 0% | 3 | 0 | W03-05 | Finlay | 19 | On Track
W03-10 | Technical Design | 3 | Security | Create role and permission matrix | Users, verified editors, moderators, admins and workers are separated | 2026-08-31 | 2026-09-06 | Critical | Not Started | 0% | 2 | 0 | W03-09 | Finlay | 19 | On Track
W03-11 | Technical Design | 3 | Security | Create football-specific threat model | Assets, actors, abuse cases, controls and residual risks are documented | 2026-08-31 | 2026-09-06 | Critical | Not Started | 0% | 4 | 0 | W01-14 | Finlay | 19 | On Track
W03-12 | Technical Design | 3 | Safety | Design moderation and appeal workflow | Reports, cases, actions, evidence, audit and appeals are linked | 2026-08-31 | 2026-09-06 | Critical | Not Started | 0% | 3 | 0 | W03-10 | Finlay | 19 | On Track
W03-13 | Technical Design | 3 | ML | Write ML experiment specification | Target, features, timestamps, splits, metrics and limitations are defined | 2026-08-31 | 2026-09-06 | Critical | Not Started | 0% | 3 | 0 | W03-02 | Finlay | 19 | On Track
W03-14 | Technical Design | 3 | Testing | Write initial testing strategy | Unit, integration, contract, E2E, security, accessibility and ML tests are mapped | 2026-08-31 | 2026-09-06 | Critical | Not Started | 0% | 3 | 0 | W01-16 | Finlay | 19 | On Track
W03-15 | Technical Design | 3 | Documentation | Record initial architecture decisions | Stack, database, live updates and deployment decisions have ADRs | 2026-08-31 | 2026-09-06 | High | Not Started | 0% | 2 | 0 | W03-05 | Finlay | 19 | On Track
W04-01 | Foundation & Data | 4 | Engineering | Initialise frontend and backend applications | Both applications run locally with documented commands | 2026-09-07 | 2026-09-13 | Critical | Not Started | 0% | 3 | 0 | W03-15 | Finlay | 26 | On Track
W04-02 | Foundation & Data | 4 | Engineering | Configure TypeScript, formatting and linting | Consistent checks run locally and in CI | 2026-09-07 | 2026-09-13 | High | Not Started | 0% | 2 | 0 | W04-01 | Finlay | 26 | On Track
W04-03 | Foundation & Data | 4 | DevOps | Create environment configuration strategy | Local, test and production values are separated safely | 2026-09-07 | 2026-09-13 | Critical | Not Started | 0% | 2 | 0 | W04-01 | Finlay | 26 | On Track
W04-04 | Foundation & Data | 4 | DevOps | Create Docker development environment | Application and dependencies start reproducibly | 2026-09-07 | 2026-09-13 | High | Not Started | 0% | 4 | 0 | W04-03 | Finlay | 26 | On Track
W04-05 | Foundation & Data | 4 | Data | Connect PostgreSQL and migration tooling | Database connection and repeatable migrations work | 2026-09-07 | 2026-09-13 | Critical | Not Started | 0% | 4 | 0 | W04-01 | Finlay | 26 | On Track
W04-06 | Foundation & Data | 4 | Data | Create initial football and user migrations | Competition, team, player, membership, fixture, event and user tables exist | 2026-09-07 | 2026-09-13 | Critical | Not Started | 0% | 5 | 0 | W04-05 | Finlay | 26 | On Track
W04-07 | Foundation & Data | 4 | Data | Create deterministic seed-data system | Demo database can be rebuilt without private credentials | 2026-09-07 | 2026-09-13 | High | Not Started | 0% | 3 | 0 | W04-06 | Finlay | 26 | On Track
W04-08 | Foundation & Data | 4 | Testing | Configure frontend, backend and database tests | Test commands run successfully in a clean environment | 2026-09-07 | 2026-09-13 | Critical | Not Started | 0% | 3 | 0 | W04-01 | Finlay | 26 | On Track
W04-09 | Foundation & Data | 4 | DevOps | Create continuous-integration workflow | Linting, tests and migrations run on every change | 2026-09-07 | 2026-09-13 | Critical | Not Started | 0% | 3 | 0 | W04-02 | Finlay | 26 | On Track
W04-10 | Foundation & Data | 4 | Backend | Implement validation and structured errors | Invalid requests return consistent safe responses | 2026-09-07 | 2026-09-13 | High | Not Started | 0% | 3 | 0 | W04-01 | Finlay | 26 | On Track
W04-11 | Foundation & Data | 4 | Observability | Implement health checks and structured logging | Service health and failures can be diagnosed | 2026-09-07 | 2026-09-13 | High | Not Started | 0% | 2.5 | 0 | W04-01 | Finlay | 26 | On Track
W04-12 | Foundation & Data | 4 | Documentation | Write reproducible setup guide | A new developer can start the project from the README | 2026-09-07 | 2026-09-13 | Critical | Not Started | 0% | 2 | 0 | W04-04 | Finlay | 26 | On Track
W05-01 | Foundation & Data | 5 | Research | Select provider and initial competition | Decision is supported by data completeness, licence and cost evidence | 2026-09-14 | 2026-09-20 | Critical | Not Started | 0% | 2 | 0 | W01-10 | Finlay | 33 | On Track
W05-02 | Foundation & Data | 5 | Backend | Implement provider adapter boundary | Provider-specific formats do not leak into domain services | 2026-09-14 | 2026-09-20 | Critical | Not Started | 0% | 4 | 0 | W05-01 | Finlay | 33 | On Track
W05-03 | Foundation & Data | 5 | Data | Implement external ID mappings | Repeated imports resolve to stable internal entities | 2026-09-14 | 2026-09-20 | Critical | Not Started | 0% | 3 | 0 | W05-02 | Finlay | 33 | On Track
W05-04 | Foundation & Data | 5 | Backend | Implement competition and season ingestion | Selected competition and season import correctly | 2026-09-14 | 2026-09-20 | High | Not Started | 0% | 3 | 0 | W05-03 | Finlay | 33 | On Track
W05-05 | Foundation & Data | 5 | Backend | Implement team, player and membership ingestion | Squad relationships preserve effective dates | 2026-09-14 | 2026-09-20 | Critical | Not Started | 0% | 5 | 0 | W05-03 | Finlay | 33 | On Track
W05-06 | Foundation & Data | 5 | Backend | Implement fixture, result and event ingestion | Scheduled and completed matches import correctly | 2026-09-14 | 2026-09-20 | Critical | Not Started | 0% | 5 | 0 | W05-03 | Finlay | 33 | On Track
W05-07 | Foundation & Data | 5 | Backend | Implement standings ingestion | League table data maps to internal teams and season | 2026-09-14 | 2026-09-20 | High | Not Started | 0% | 3 | 0 | W05-03 | Finlay | 33 | On Track
W05-08 | Foundation & Data | 5 | Jobs | Create scheduled ingestion worker | Refresh frequency respects provider limits | 2026-09-14 | 2026-09-20 | Critical | Not Started | 0% | 4 | 0 | W05-06 | Finlay | 33 | On Track
W05-09 | Foundation & Data | 5 | Data | Validate provider responses and missing fields | Invalid records are rejected or quarantined with clear logs | 2026-09-14 | 2026-09-20 | Critical | Not Started | 0% | 3 | 0 | W05-02 | Finlay | 33 | On Track
W05-10 | Foundation & Data | 5 | Reliability | Implement idempotent updates and corrections | Retries and corrected events do not create duplicates | 2026-09-14 | 2026-09-20 | Critical | Not Started | 0% | 5 | 0 | W05-06 | Finlay | 33 | On Track
W05-11 | Foundation & Data | 5 | Reliability | Add freshness and provider-outage handling | Pages show last update and degrade without corrupting data | 2026-09-14 | 2026-09-20 | High | Not Started | 0% | 3 | 0 | W05-08 | Finlay | 33 | On Track
W05-12 | Foundation & Data | 5 | Testing | Add provider contract and ingestion tests | Recorded fixtures cover normal, missing, repeated and corrected data | 2026-09-14 | 2026-09-20 | Critical | Not Started | 0% | 4 | 0 | W05-10 | Finlay | 33 | On Track
W06-01 | Football Core | 6 | Frontend | Build match list and date navigation | Users can browse fixtures and results by date | 2026-09-21 | 2026-09-27 | Critical | Not Started | 0% | 4 | 0 | W05-06 | Finlay | 40 | On Track
W06-02 | Football Core | 6 | Frontend | Build competition overview and fixtures | Competition information and fixture groups are usable | 2026-09-21 | 2026-09-27 | High | Not Started | 0% | 3 | 0 | W06-01 | Finlay | 40 | On Track
W06-03 | Football Core | 6 | Frontend | Build league table | Positions, points, form and qualification states display correctly | 2026-09-21 | 2026-09-27 | Critical | Not Started | 0% | 4 | 0 | W05-07 | Finlay | 40 | On Track
W06-04 | Football Core | 6 | Frontend | Build team overview page | Team information, form and upcoming matches display | 2026-09-21 | 2026-09-27 | Critical | Not Started | 0% | 4 | 0 | W05-05 | Finlay | 40 | On Track
W06-05 | Football Core | 6 | Frontend | Build team fixture and result history | Historical matches paginate and filter correctly | 2026-09-21 | 2026-09-27 | High | Not Started | 0% | 3 | 0 | W06-04 | Finlay | 40 | On Track
W06-06 | Football Core | 6 | Frontend | Build squad display | Current membership and player positions display correctly | 2026-09-21 | 2026-09-27 | High | Not Started | 0% | 3 | 0 | W05-05 | Finlay | 40 | On Track
W06-07 | Football Core | 6 | Frontend | Build player overview and career history | Player information and time-bounded team history display | 2026-09-21 | 2026-09-27 | Critical | Not Started | 0% | 4 | 0 | W05-05 | Finlay | 40 | On Track
W06-08 | Football Core | 6 | Search | Implement team, player and competition search | Search returns relevant results and handles no-result states | 2026-09-21 | 2026-09-27 | High | Not Started | 0% | 4 | 0 | W06-04 | Finlay | 40 | On Track
W06-09 | Football Core | 6 | UX | Implement loading, empty and provider-error states | All football pages remain understandable without ideal data | 2026-09-21 | 2026-09-27 | Critical | Not Started | 0% | 3 | 0 | W05-11 | Finlay | 40 | On Track
W06-10 | Football Core | 6 | Accessibility | Make football pages responsive and keyboard usable | Core journeys work on mobile, desktop and keyboard | 2026-09-21 | 2026-09-27 | Critical | Not Started | 0% | 4 | 0 | W06-01 | Finlay | 40 | On Track
W06-11 | Football Core | 6 | Testing | Test standings, memberships and football queries | Unit and integration coverage includes historical transfers | 2026-09-21 | 2026-09-27 | Critical | Not Started | 0% | 4 | 0 | W06-03 | Finlay | 40 | On Track
W07-01 | Football Core | 7 | Frontend | Build scheduled and pre-match states | Kick-off, venue, prediction placeholder and line-up availability display | 2026-09-28 | 2026-10-04 | Critical | Not Started | 0% | 3 | 0 | W06-01 | Finlay | 47 | On Track
W07-02 | Football Core | 7 | Frontend | Build live, half-time and final match states | Score, clock and status update without confusing the user | 2026-09-28 | 2026-10-04 | Critical | Not Started | 0% | 5 | 0 | W07-01 | Finlay | 47 | On Track
W07-03 | Football Core | 7 | Frontend | Build postponed, cancelled and abandoned states | Exceptional match states have accurate messaging | 2026-09-28 | 2026-10-04 | High | Not Started | 0% | 3 | 0 | W07-01 | Finlay | 47 | On Track
W07-04 | Football Core | 7 | Frontend | Build match event timeline | Goals, cards and substitutions appear in correct order | 2026-09-28 | 2026-10-04 | Critical | Not Started | 0% | 4 | 0 | W05-06 | Finlay | 47 | On Track
W07-05 | Football Core | 7 | Frontend | Build line-up and formation display | Starting players, substitutes and formation are readable | 2026-09-28 | 2026-10-04 | High | Not Started | 0% | 4 | 0 | W05-05 | Finlay | 47 | On Track
W07-06 | Football Core | 7 | Frontend | Build match statistics display | Available statistics distinguish missing from zero | 2026-09-28 | 2026-10-04 | High | Not Started | 0% | 3 | 0 | W05-06 | Finlay | 47 | On Track
W07-07 | Football Core | 7 | Backend | Implement safe live-update transport | Polling or streaming updates clients within selected limits | 2026-09-28 | 2026-10-04 | Critical | Not Started | 0% | 5 | 0 | W05-08 | Finlay | 47 | On Track
W07-08 | Football Core | 7 | Reliability | Display source freshness and stale-data state | Users can see when live information may be delayed | 2026-09-28 | 2026-10-04 | Critical | Not Started | 0% | 2 | 0 | W05-11 | Finlay | 47 | On Track
W07-09 | Football Core | 7 | Testing | Simulate goals, corrections and duplicate events | Repeated or corrected events remain consistent | 2026-09-28 | 2026-10-04 | Critical | Not Started | 0% | 4 | 0 | W05-10 | Finlay | 47 | On Track
W07-10 | Football Core | 7 | Testing | Simulate postponement and provider outage | Match centre degrades safely and recovers | 2026-09-28 | 2026-10-04 | High | Not Started | 0% | 3 | 0 | W05-11 | Finlay | 47 | On Track
W07-11 | Football Core | 7 | Accessibility | Test live updates with keyboard and assistive labels | Live changes do not move focus and have text alternatives | 2026-09-28 | 2026-10-04 | Critical | Not Started | 0% | 3 | 0 | W07-02 | Finlay | 47 | On Track
W08-01 | Accounts & Community | 8 | Authentication | Implement registration and email verification | New accounts verify ownership before sensitive actions | 2026-10-05 | 2026-10-11 | Critical | Not Started | 0% | 5 | 0 | W04-10 | Finlay | 54 | On Track
W08-02 | Accounts & Community | 8 | Authentication | Implement login and logout | Sessions start and end securely | 2026-10-05 | 2026-10-11 | Critical | Not Started | 0% | 3 | 0 | W08-01 | Finlay | 54 | On Track
W08-03 | Accounts & Community | 8 | Authentication | Implement password recovery | Single-use expiring reset flow works safely | 2026-10-05 | 2026-10-11 | Critical | Not Started | 0% | 4 | 0 | W08-01 | Finlay | 54 | On Track
W08-04 | Accounts & Community | 8 | Security | Implement secure session management | Secure cookies, expiry and session revocation are applied | 2026-10-05 | 2026-10-11 | Critical | Not Started | 0% | 4 | 0 | W08-02 | Finlay | 54 | On Track
W08-05 | Accounts & Community | 8 | Profiles | Implement public profile creation and editing | Public identity is separated from private account data | 2026-10-05 | 2026-10-11 | High | Not Started | 0% | 4 | 0 | W08-01 | Finlay | 54 | On Track
W08-06 | Accounts & Community | 8 | Personalisation | Implement team follows | Users can follow and unfollow teams consistently | 2026-10-05 | 2026-10-11 | Critical | Not Started | 0% | 3 | 0 | W08-01 | Finlay | 54 | On Track
W08-07 | Accounts & Community | 8 | Personalisation | Implement player and user follows | Follow relationships enforce blocks and uniqueness | 2026-10-05 | 2026-10-11 | High | Not Started | 0% | 4 | 0 | W08-06 | Finlay | 54 | On Track
W08-08 | Accounts & Community | 8 | Personalisation | Implement favourite matches | Users can save upcoming or live matches | 2026-10-05 | 2026-10-11 | Medium | Not Started | 0% | 2.5 | 0 | W08-01 | Finlay | 54 | On Track
W08-09 | Accounts & Community | 8 | Personalisation | Build Following feed foundation | Followed football entities and accounts influence feed results | 2026-10-05 | 2026-10-11 | Critical | Not Started | 0% | 4 | 0 | W08-06 | Finlay | 54 | On Track
W08-10 | Accounts & Community | 8 | Notifications | Build notification preference settings | Users control team, match, event type and channel | 2026-10-05 | 2026-10-11 | Critical | Not Started | 0% | 4 | 0 | W08-06 | Finlay | 54 | On Track
W08-11 | Accounts & Community | 8 | Security | Add authentication rate limits and validation | Brute-force and malformed requests are constrained | 2026-10-05 | 2026-10-11 | Critical | Not Started | 0% | 3 | 0 | W08-02 | Finlay | 54 | On Track
W08-12 | Accounts & Community | 8 | Testing | Add authentication and permission tests | Registration, recovery, sessions and protected routes are covered | 2026-10-05 | 2026-10-11 | Critical | Not Started | 0% | 5 | 0 | W08-04 | Finlay | 54 | On Track
W09-01 | Accounts & Community | 9 | Social | Create post and content models | Posts support ownership, visibility, lifecycle and football references | 2026-10-12 | 2026-10-18 | Critical | Not Started | 0% | 4 | 0 | W03-01 | Finlay | 61 | On Track
W09-02 | Accounts & Community | 9 | Social | Implement match discussions | Every supported fixture has a controlled discussion space | 2026-10-12 | 2026-10-18 | Critical | Not Started | 0% | 5 | 0 | W09-01 | Finlay | 61 | On Track
W09-03 | Accounts & Community | 9 | Social | Implement comments and limited replies | Thread depth and permissions are enforced | 2026-10-12 | 2026-10-18 | High | Not Started | 0% | 4 | 0 | W09-01 | Finlay | 61 | On Track
W09-04 | Accounts & Community | 9 | Social | Implement reactions | Reactions are unique, reversible and count accurately | 2026-10-12 | 2026-10-18 | Medium | Not Started | 0% | 3 | 0 | W09-01 | Finlay | 61 | On Track
W09-05 | Accounts & Community | 9 | Social | Build supporter profile content views | Posts and replies display with privacy and moderation states | 2026-10-12 | 2026-10-18 | High | Not Started | 0% | 3 | 0 | W08-05 | Finlay | 61 | On Track
W09-06 | Accounts & Community | 9 | Feed | Implement initial For You feed rules | Transparent signals create a useful non-ML feed | 2026-10-12 | 2026-10-18 | Critical | Not Started | 0% | 5 | 0 | W09-01 | Finlay | 61 | On Track
W09-07 | Accounts & Community | 9 | Feed | Complete Following feed | Followed accounts and football entities appear predictably | 2026-10-12 | 2026-10-18 | Critical | Not Started | 0% | 4 | 0 | W08-09 | Finlay | 61 | On Track
W09-08 | Accounts & Community | 9 | Frontend | Add community tabs to match, team and player pages | Social content remains separate from canonical information | 2026-10-12 | 2026-10-18 | Critical | Not Started | 0% | 4 | 0 | W09-02 | Finlay | 61 | On Track
W09-09 | Accounts & Community | 9 | Privacy | Implement content deletion and visibility states | Deleted, hidden, restricted and archived states behave distinctly | 2026-10-12 | 2026-10-18 | Critical | Not Started | 0% | 4 | 0 | W03-04 | Finlay | 61 | On Track
W09-10 | Accounts & Community | 9 | Privacy | Implement match-discussion archival lifecycle | Thread closes, archives and expires according to configuration | 2026-10-12 | 2026-10-18 | High | Not Started | 0% | 4 | 0 | W09-09 | Finlay | 61 | On Track
W09-11 | Accounts & Community | 9 | Performance | Implement feed and discussion pagination | Large feeds load incrementally and consistently | 2026-10-12 | 2026-10-18 | High | Not Started | 0% | 3 | 0 | W09-06 | Finlay | 61 | On Track
W09-12 | Accounts & Community | 9 | Testing | Test content permissions and lifecycle | Blocks, deletions, archives and pagination have coverage | 2026-10-12 | 2026-10-18 | Critical | Not Started | 0% | 5 | 0 | W09-09 | Finlay | 61 | On Track
W10-01 | Accounts & Community | 10 | Safety | Implement reporting for content and accounts | Reports capture category, target, context and reporter | 2026-10-19 | 2026-10-25 | Critical | Not Started | 0% | 5 | 0 | W09-01 | Finlay | 68 | On Track
W10-02 | Accounts & Community | 10 | Safety | Implement block and mute | Blocked users cannot bypass restrictions through replies or follows | 2026-10-19 | 2026-10-25 | Critical | Not Started | 0% | 4 | 0 | W09-03 | Finlay | 68 | On Track
W10-03 | Accounts & Community | 10 | Safety | Implement match-thread slow mode and locking | Authorised moderators can control high-risk discussions | 2026-10-19 | 2026-10-25 | High | Not Started | 0% | 4 | 0 | W09-02 | Finlay | 68 | On Track
W10-04 | Accounts & Community | 10 | Safety | Implement reply restrictions | Threads can limit replies without deleting football information | 2026-10-19 | 2026-10-25 | High | Not Started | 0% | 3 | 0 | W10-03 | Finlay | 68 | On Track
W10-05 | Accounts & Community | 10 | Moderation | Build moderator review queue | Cases sort by priority, age, match and risk category | 2026-10-19 | 2026-10-25 | Critical | Not Started | 0% | 5 | 0 | W10-01 | Finlay | 68 | On Track
W10-06 | Accounts & Community | 10 | Moderation | Implement content removal and restoration | Public visibility changes without destroying evidence | 2026-10-19 | 2026-10-25 | Critical | Not Started | 0% | 4 | 0 | W10-05 | Finlay | 68 | On Track
W10-07 | Accounts & Community | 10 | Moderation | Implement warnings and temporary restrictions | Actions include reason, duration and affected capability | 2026-10-19 | 2026-10-25 | Critical | Not Started | 0% | 4 | 0 | W10-05 | Finlay | 68 | On Track
W10-08 | Accounts & Community | 10 | Moderation | Implement suspension, ban and revocation | Severe actions are role-restricted and reviewable | 2026-10-19 | 2026-10-25 | Critical | Not Started | 0% | 4 | 0 | W10-05 | Finlay | 68 | On Track
W10-09 | Accounts & Community | 10 | Moderation | Implement immutable moderation audit history | Every moderator action records actor, reason and timestamp | 2026-10-19 | 2026-10-25 | Critical | Not Started | 0% | 5 | 0 | W10-05 | Finlay | 68 | On Track
W10-10 | Accounts & Community | 10 | Moderation | Implement user appeals | Eligible users can appeal and receive an outcome | 2026-10-19 | 2026-10-25 | High | Not Started | 0% | 4 | 0 | W10-07 | Finlay | 68 | On Track
W10-11 | Accounts & Community | 10 | Documentation | Write Community Guidelines and taxonomy | Permitted rivalry and prohibited harms are clearly distinguished | 2026-10-19 | 2026-10-25 | Critical | Not Started | 0% | 4 | 0 | W01-13 | Finlay | 68 | On Track
W10-12 | Accounts & Community | 10 | Documentation | Write moderation matrix and enforcement policy | Comparable cases lead to consistent initial decisions | 2026-10-19 | 2026-10-25 | Critical | Not Started | 0% | 4 | 0 | W10-11 | Finlay | 68 | On Track
W10-13 | Accounts & Community | 10 | Documentation | Write matchday incident and appeals procedures | Urgent escalation and routine appeals have defined owners | 2026-10-19 | 2026-10-25 | High | Not Started | 0% | 3 | 0 | W10-11 | Finlay | 68 | On Track
W10-14 | Accounts & Community | 10 | Testing | Test moderator permissions, blocks and audit | Moderators cannot exceed roles or alter historical audit entries | 2026-10-19 | 2026-10-25 | Critical | Not Started | 0% | 5 | 0 | W10-09 | Finlay | 68 | On Track
W11-01 | ML & Notifications | 11 | ML | Extract historical match dataset | Dataset contains stable match IDs and as-of timestamps | 2026-10-26 | 2026-11-01 | Critical | Not Started | 0% | 5 | 0 | W05-01 | Finlay | 75 | On Track
W11-02 | ML & Notifications | 11 | ML | Clean and validate model data | Missingness, duplicates and invalid outcomes are documented | 2026-10-26 | 2026-11-01 | Critical | Not Started | 0% | 4 | 0 | W11-01 | Finlay | 75 | On Track
W11-03 | ML & Notifications | 11 | ML | Create time-aware feature pipeline | Every feature is reproducible at the prediction timestamp | 2026-10-26 | 2026-11-01 | Critical | Not Started | 0% | 5 | 0 | W11-02 | Finlay | 75 | On Track
W11-04 | ML & Notifications | 11 | ML | Implement historical-frequency baseline | Simple home/draw/away baseline is evaluated | 2026-10-26 | 2026-11-01 | High | Not Started | 0% | 2 | 0 | W11-02 | Finlay | 75 | On Track
W11-05 | ML & Notifications | 11 | ML | Implement home-advantage baseline | Venue effect baseline is evaluated and recorded | 2026-10-26 | 2026-11-01 | High | Not Started | 0% | 2 | 0 | W11-02 | Finlay | 75 | On Track
W11-06 | ML & Notifications | 11 | ML | Implement Elo or logistic baseline | Transparent team-strength model produces probabilities | 2026-10-26 | 2026-11-01 | Critical | Not Started | 0% | 5 | 0 | W11-03 | Finlay | 75 | On Track
W11-07 | ML & Notifications | 11 | ML | Create chronological train, validation and test split | No future match can influence an earlier split | 2026-10-26 | 2026-11-01 | Critical | Not Started | 0% | 3 | 0 | W11-01 | Finlay | 75 | On Track
W11-08 | ML & Notifications | 11 | ML | Evaluate accuracy and class performance | Home, draw and away results are reported separately | 2026-10-26 | 2026-11-01 | High | Not Started | 0% | 2 | 0 | W11-06 | Finlay | 75 | On Track
W11-09 | ML & Notifications | 11 | ML | Evaluate log loss, Brier score and calibration | Probability quality is compared across baselines | 2026-10-26 | 2026-11-01 | Critical | Not Started | 0% | 3 | 0 | W11-06 | Finlay | 75 | On Track
W11-10 | ML & Notifications | 11 | Testing | Test feature timestamps for leakage | Known future fields fail automated leakage checks | 2026-10-26 | 2026-11-01 | Critical | Not Started | 0% | 4 | 0 | W11-03 | Finlay | 75 | On Track
W11-11 | ML & Notifications | 11 | Documentation | Write dataset description and experiment log | Sources, transformations, exclusions and results are reproducible | 2026-10-26 | 2026-11-01 | Critical | Not Started | 0% | 3 | 0 | W11-09 | Finlay | 75 | On Track
W11-12 | ML & Notifications | 11 | Documentation | Record baseline limitations | Data gaps and expected failure conditions are explicit | 2026-10-26 | 2026-11-01 | High | Not Started | 0% | 2 | 0 | W11-09 | Finlay | 75 | On Track
W12-01 | ML & Notifications | 12 | ML | Add recent team form and opponent-quality features | Features use only matches completed before prediction time | 2026-11-02 | 2026-11-08 | Critical | Not Started | 0% | 4 | 0 | W11-03 | Finlay | 82 | On Track
W12-02 | ML & Notifications | 12 | ML | Add rest and fixture-congestion features | Rest calculations handle postponements and missing matches | 2026-11-02 | 2026-11-08 | High | Not Started | 0% | 3 | 0 | W11-03 | Finlay | 82 | On Track
W12-03 | ML & Notifications | 12 | ML | Evaluate line-up and player availability | Feasibility and missingness are measured before use | 2026-11-02 | 2026-11-08 | High | Not Started | 0% | 3 | 0 | W11-02 | Finlay | 82 | On Track
W12-04 | ML & Notifications | 12 | ML | Train improved tabular model | Candidate model is tuned only on training/validation periods | 2026-11-02 | 2026-11-08 | Critical | Not Started | 0% | 5 | 0 | W12-01 | Finlay | 82 | On Track
W12-05 | ML & Notifications | 12 | ML | Compare improved model with all baselines | Improvement is reproducible and not selected from test leakage | 2026-11-02 | 2026-11-08 | Critical | Not Started | 0% | 4 | 0 | W12-04 | Finlay | 82 | On Track
W12-06 | ML & Notifications | 12 | Backend | Create prediction API | Match prediction response includes probabilities, time and model version | 2026-11-02 | 2026-11-08 | Critical | Not Started | 0% | 4 | 0 | W12-05 | Finlay | 82 | On Track
W12-07 | ML & Notifications | 12 | Data | Store model versions and prediction snapshots | Historical predictions can be reproduced and audited | 2026-11-02 | 2026-11-08 | Critical | Not Started | 0% | 3 | 0 | W12-06 | Finlay | 82 | On Track
W12-08 | ML & Notifications | 12 | ML | Implement pre-line-up and confirmed-line-up states | UI and API identify available information at each prediction | 2026-11-02 | 2026-11-08 | High | Not Started | 0% | 4 | 0 | W12-06 | Finlay | 82 | On Track
W12-09 | ML & Notifications | 12 | ML | Generate plain-language influential factors | Factors are faithful, understandable and non-deterministic | 2026-11-02 | 2026-11-08 | Critical | Not Started | 0% | 4 | 0 | W12-05 | Finlay | 82 | On Track
W12-10 | ML & Notifications | 12 | Frontend | Build match prediction component | Probabilities, time, line-up state and limitations are displayed | 2026-11-02 | 2026-11-08 | Critical | Not Started | 0% | 4 | 0 | W12-06 | Finlay | 82 | On Track
W12-11 | ML & Notifications | 12 | Documentation | Write model card | Purpose, data, metrics, limitations and responsible presentation are documented | 2026-11-02 | 2026-11-08 | Critical | Not Started | 0% | 4 | 0 | W12-05 | Finlay | 82 | On Track
W12-12 | ML & Notifications | 12 | Testing | Test prediction reproducibility and presentation | Snapshots reproduce and probabilities/labels remain consistent | 2026-11-02 | 2026-11-08 | Critical | Not Started | 0% | 4 | 0 | W12-07 | Finlay | 82 | On Track
W13-01 | ML & Notifications | 13 | Notifications | Implement match-reminder email | Opted-in users receive one correctly timed reminder | 2026-11-09 | 2026-11-15 | High | Not Started | 0% | 4 | 0 | W08-10 | Finlay | 89 | On Track
W13-02 | ML & Notifications | 13 | Notifications | Implement line-up and kick-off alerts | Alerts respect team, match and channel preferences | 2026-11-09 | 2026-11-15 | High | Not Started | 0% | 4 | 0 | W13-01 | Finlay | 89 | On Track
W13-03 | ML & Notifications | 13 | Notifications | Implement goal notifications | Goals generate one alert with match and scorer context | 2026-11-09 | 2026-11-15 | Critical | Not Started | 0% | 5 | 0 | W07-09 | Finlay | 89 | On Track
W13-04 | ML & Notifications | 13 | Notifications | Implement half-time and full-time alerts | Users receive enabled summary states once | 2026-11-09 | 2026-11-15 | High | Not Started | 0% | 3 | 0 | W13-03 | Finlay | 89 | On Track
W13-05 | ML & Notifications | 13 | Notifications | Implement postponement and cancellation alerts | Material schedule changes notify affected followers | 2026-11-09 | 2026-11-15 | High | Not Started | 0% | 3 | 0 | W07-03 | Finlay | 89 | On Track
W13-06 | ML & Notifications | 13 | Notifications | Implement social and moderation notifications | Replies, mentions and case outcomes respect preferences | 2026-11-09 | 2026-11-15 | Medium | Not Started | 0% | 4 | 0 | W10-10 | Finlay | 89 | On Track
W13-07 | ML & Notifications | 13 | Notifications | Create delivery logs and retry handling | Failures retry safely and remain diagnosable | 2026-11-09 | 2026-11-15 | Critical | Not Started | 0% | 4 | 0 | W03-07 | Finlay | 89 | On Track
W13-08 | ML & Notifications | 13 | Reliability | Implement notification idempotency | Repeated or corrected provider events do not duplicate alerts | 2026-11-09 | 2026-11-15 | Critical | Not Started | 0% | 5 | 0 | W13-07 | Finlay | 89 | On Track
W13-09 | ML & Notifications | 13 | External Links | Build region-aware Where to Watch section | Only reliable official listings are shown with region context | 2026-11-09 | 2026-11-15 | High | Not Started | 0% | 4 | 0 | W01-13 | Finlay | 89 | On Track
W13-10 | ML & Notifications | 13 | External Links | Add official team ticket links | Links use approved sources and do not invent availability | 2026-11-09 | 2026-11-15 | High | Not Started | 0% | 3 | 0 | W13-09 | Finlay | 89 | On Track
W13-11 | ML & Notifications | 13 | Security | Implement approved-domain and URL validation | Unapproved or malformed official links cannot be published | 2026-11-09 | 2026-11-15 | Critical | Not Started | 0% | 4 | 0 | W13-09 | Finlay | 89 | On Track
W13-12 | ML & Notifications | 13 | External Links | Add last-verified and broken-link handling | Users can see freshness and receive safe fallbacks | 2026-11-09 | 2026-11-15 | High | Not Started | 0% | 3 | 0 | W13-11 | Finlay | 89 | On Track
W13-13 | ML & Notifications | 13 | Testing | Test alert preferences, duplicates and failures | Disabled alerts stay disabled and retries do not duplicate | 2026-11-09 | 2026-11-15 | Critical | Not Started | 0% | 5 | 0 | W13-08 | Finlay | 89 | On Track
W14-01 | Release & Portfolio | 14 | Testing | Run complete P0 end-to-end journey suite | Registration through match, discussion, report and prediction passes | 2026-11-16 | 2026-11-22 | Critical | Not Started | 0% | 6 | 0 | W13-13 | Finlay | 96 | On Track
W14-02 | Release & Portfolio | 14 | Performance | Profile and index database queries | Slow fixture, table, feed and moderation queries are improved | 2026-11-16 | 2026-11-22 | Critical | Not Started | 0% | 5 | 0 | W14-01 | Finlay | 96 | On Track
W14-03 | Release & Portfolio | 14 | Performance | Optimise feed and discussion pagination | Large datasets maintain stable latency and ordering | 2026-11-16 | 2026-11-22 | High | Not Started | 0% | 4 | 0 | W09-11 | Finlay | 96 | On Track
W14-04 | Release & Portfolio | 14 | Performance | Implement and validate caching strategy | Cache improves reads without serving incorrect score states | 2026-11-16 | 2026-11-22 | Critical | Not Started | 0% | 5 | 0 | W14-02 | Finlay | 96 | On Track
W14-05 | Release & Portfolio | 14 | Reliability | Tune provider polling and worker queues | Rate limits, retries and backlogs remain controlled | 2026-11-16 | 2026-11-22 | High | Not Started | 0% | 4 | 0 | W05-08 | Finlay | 96 | On Track
W14-06 | Release & Portfolio | 14 | Performance | Optimise notification delivery pipeline | Matchday fan-out meets chosen performance target | 2026-11-16 | 2026-11-22 | High | Not Started | 0% | 4 | 0 | W13-08 | Finlay | 96 | On Track
W14-07 | Release & Portfolio | 14 | Frontend | Optimise images and frontend bundle | Core pages load efficiently on typical mobile connections | 2026-11-16 | 2026-11-22 | High | Not Started | 0% | 4 | 0 | W14-01 | Finlay | 96 | On Track
W14-08 | Release & Portfolio | 14 | Accessibility | Complete keyboard and focus audit | All P0 journeys work without a mouse | 2026-11-16 | 2026-11-22 | Critical | Not Started | 0% | 4 | 0 | W14-01 | Finlay | 96 | On Track
W14-09 | Release & Portfolio | 14 | Accessibility | Complete contrast and text-label audit | Information never relies only on colour | 2026-11-16 | 2026-11-22 | Critical | Not Started | 0% | 3 | 0 | W14-01 | Finlay | 96 | On Track
W14-10 | Release & Portfolio | 14 | Accessibility | Test live announcements and reduced motion | Live updates are understandable and controllable | 2026-11-16 | 2026-11-22 | Critical | Not Started | 0% | 4 | 0 | W07-11 | Finlay | 96 | On Track
W14-11 | Release & Portfolio | 14 | Responsive Design | Test mobile, tablet and desktop layouts | No P0 screen clips or loses essential actions | 2026-11-16 | 2026-11-22 | Critical | Not Started | 0% | 4 | 0 | W14-01 | Finlay | 96 | On Track
W14-12 | Release & Portfolio | 14 | Testing | Run initial matchday load test | Results identify capacity, bottlenecks and safe degradation | 2026-11-16 | 2026-11-22 | High | Not Started | 0% | 5 | 0 | W14-04 | Finlay | 96 | On Track
W15-01 | Release & Portfolio | 15 | Security | Test authentication and account recovery | Common takeover and reset abuse paths are constrained | 2026-11-23 | 2026-11-29 | Critical | Not Started | 0% | 5 | 0 | W08-12 | Finlay | 103 | On Track
W15-02 | Release & Portfolio | 15 | Security | Test role and object-level authorisation | Users and moderators cannot access unauthorised resources | 2026-11-23 | 2026-11-29 | Critical | Not Started | 0% | 5 | 0 | W10-14 | Finlay | 103 | On Track
W15-03 | Release & Portfolio | 15 | Security | Test injection, XSS and request forgery | Inputs, rendering and state changes resist common attacks | 2026-11-23 | 2026-11-29 | Critical | Not Started | 0% | 5 | 0 | W15-02 | Finlay | 103 | On Track
W15-04 | Release & Portfolio | 15 | Security | Test sessions, rate limits and malicious links | Session boundaries and anti-abuse controls behave correctly | 2026-11-23 | 2026-11-29 | Critical | Not Started | 0% | 4 | 0 | W13-11 | Finlay | 103 | On Track
W15-05 | Release & Portfolio | 15 | Security | Run dependency and secret scans | No unresolved critical dependency or committed secret remains | 2026-11-23 | 2026-11-29 | Critical | Not Started | 0% | 3 | 0 | W04-09 | Finlay | 103 | On Track
W15-06 | Release & Portfolio | 15 | Security | Review moderator and administrator permissions | Least privilege and strong audit coverage are demonstrated | 2026-11-23 | 2026-11-29 | Critical | Not Started | 0% | 3 | 0 | W10-14 | Finlay | 103 | On Track
W15-07 | Release & Portfolio | 15 | Reliability | Test backup and database restoration | A documented backup restores to a usable environment | 2026-11-23 | 2026-11-29 | Critical | Not Started | 0% | 4 | 0 | W04-05 | Finlay | 103 | On Track
W15-08 | Release & Portfolio | 15 | Reliability | Test provider and notification outages | Failures degrade safely and recover without duplicate data | 2026-11-23 | 2026-11-29 | Critical | Not Started | 0% | 4 | 0 | W13-13 | Finlay | 103 | On Track
W15-09 | Release & Portfolio | 15 | Testing | Run full unit, integration and API contract suites | All critical suites pass in CI | 2026-11-23 | 2026-11-29 | Critical | Not Started | 0% | 5 | 0 | W14-01 | Finlay | 103 | On Track
W15-10 | Release & Portfolio | 15 | Testing | Run final E2E and accessibility suites | All P0 user journeys and accessibility gates pass | 2026-11-23 | 2026-11-29 | Critical | Not Started | 0% | 5 | 0 | W14-01 | Finlay | 103 | On Track
W15-11 | Release & Portfolio | 15 | Testing | Run final performance and ML reproducibility tests | Performance targets and model evidence are repeatable | 2026-11-23 | 2026-11-29 | High | Not Started | 0% | 5 | 0 | W14-12 | Finlay | 103 | On Track
W15-12 | Release & Portfolio | 15 | Documentation | Write security checklist and incident plan | Preventive, detection, response and recovery actions are documented | 2026-11-23 | 2026-11-29 | Critical | Not Started | 0% | 4 | 0 | W15-01 | Finlay | 103 | On Track
W15-13 | Release & Portfolio | 15 | Documentation | Write deployment runbook and limitations | Release, rollback, recovery and known gaps are explicit | 2026-11-23 | 2026-11-29 | High | Not Started | 0% | 4 | 0 | W15-07 | Finlay | 103 | On Track
W15-14 | Release & Portfolio | 15 | DevOps | Deploy and validate staging release | Release candidate runs with production-like configuration | 2026-11-23 | 2026-11-29 | Critical | Not Started | 0% | 5 | 0 | W15-09 | Finlay | 103 | On Track
W16-01 | Release & Portfolio | 16 | DevOps | Deploy production portfolio demonstration | Public demo is reachable without exposing private credentials | 2026-11-30 | 2026-12-06 | Critical | Not Started | 0% | 5 | 0 | W15-14 | Finlay | 110 | On Track
W16-02 | Release & Portfolio | 16 | Data | Create safe demonstration seed data | Demo remains understandable during provider downtime | 2026-11-30 | 2026-12-06 | High | Not Started | 0% | 3 | 0 | W16-01 | Finlay | 110 | On Track
W16-03 | Release & Portfolio | 16 | Observability | Configure monitoring and error reporting | Critical failures, jobs and provider health are visible | 2026-11-30 | 2026-12-06 | High | Not Started | 0% | 4 | 0 | W16-01 | Finlay | 110 | On Track
W16-04 | Release & Portfolio | 16 | Documentation | Complete final README and setup guide | Problem, architecture, setup, evidence and limitations are clear | 2026-11-30 | 2026-12-06 | Critical | Not Started | 0% | 5 | 0 | W15-13 | Finlay | 110 | On Track
W16-05 | Release & Portfolio | 16 | Documentation | Update architecture, ERD and API documentation | Documentation matches the deployed implementation | 2026-11-30 | 2026-12-06 | Critical | Not Started | 0% | 4 | 0 | W16-01 | Finlay | 110 | On Track
W16-06 | Release & Portfolio | 16 | Documentation | Publish final test and security report | Test scope, results, failures and residual risks are honest | 2026-11-30 | 2026-12-06 | Critical | Not Started | 0% | 4 | 0 | W15-10 | Finlay | 110 | On Track
W16-07 | Release & Portfolio | 16 | Documentation | Complete model card and evaluation report | Model evidence, baselines, calibration and limitations are complete | 2026-11-30 | 2026-12-06 | Critical | Not Started | 0% | 4 | 0 | W12-11 | Finlay | 110 | On Track
W16-08 | Release & Portfolio | 16 | Documentation | Complete community and moderation summary | Safety design and enforcement workflow are portfolio-ready | 2026-11-30 | 2026-12-06 | High | Not Started | 0% | 3 | 0 | W10-13 | Finlay | 110 | On Track
W16-09 | Release & Portfolio | 16 | Portfolio | Write project retrospective | Decisions, failures, learning and future improvements are discussed | 2026-11-30 | 2026-12-06 | High | Not Started | 0% | 3 | 0 | W16-04 | Finlay | 110 | On Track
W16-10 | Release & Portfolio | 16 | Portfolio | Capture annotated screenshots | Core football, social, safety and ML screens are represented | 2026-11-30 | 2026-12-06 | High | Not Started | 0% | 3 | 0 | W16-01 | Finlay | 110 | On Track
W16-11 | Release & Portfolio | 16 | Portfolio | Record two-to-three-minute demonstration video | Video shows one coherent end-to-end story | 2026-11-30 | 2026-12-06 | Critical | Not Started | 0% | 5 | 0 | W16-10 | Finlay | 110 | On Track
W16-12 | Release & Portfolio | 16 | Portfolio | Write CV project entry | Entry leads with outcome, technical depth and evidence | 2026-11-30 | 2026-12-06 | High | Not Started | 0% | 2 | 0 | W16-04 | Finlay | 110 | On Track
W16-13 | Release & Portfolio | 16 | Portfolio | Write portfolio case study | Problem, process, architecture, safety, ML, testing and results are covered | 2026-11-30 | 2026-12-06 | Critical | Not Started | 0% | 5 | 0 | W16-09 | Finlay | 110 | On Track
W16-14 | Release & Portfolio | 16 | Project | Complete final definition-of-done review | Every P0 item is complete or explicitly documented as incomplete | 2026-11-30 | 2026-12-06 | Critical | Not Started | 0% | 3 | 0 | W16-13 | Finlay | 110 | On Track
Formulas:
Days Remaining = IF(OR([Status]="Complete",[Status]="Deferred"),"",[Due Date]-TODAY())
Health = IF([Status]="Complete","Complete",IF([Status]="Deferred","Deferred",IF([Status]="Blocked","Blocked",IF([Due Date]<TODAY(),"Overdue",IF([Due Date]-TODAY()<=3,"Due Soon","On Track")))))

## Weekly Plan
ULTRAS — WEEKLY PLAN
Use this sheet for the weekly review. Capacity defaults to 20 hours; negative capacity gaps show where scope or dates need adjusting.
Week | Start | End | Focus | Milestone | Planned Tasks | Complete | Completion % | Est. Hours | Capacity Hours | Capacity Gap | Actual Hours | Hours Variance | Weekly Review Notes
1 | 2026-08-18 | 2026-08-23 | Research and definition | Approved P0 scope, research plan and product requirements | 17 | 2 | 11.76% | 36 | 20 | -16 | 2 | -34
2 | 2026-08-24 | 2026-08-30 | UX and interface design | Core flows, wireframes and visual system completed | 14 | 0 | 0% | 41.5 | 20 | -21.5 | 0 | -41.5
3 | 2026-08-31 | 2026-09-06 | Technical and security design | Architecture, ERD, API, threat model and test strategy approved | 15 | 0 | 0% | 47.5 | 20 | -27.5 | 0 | -47.5
4 | 2026-09-07 | 2026-09-13 | Project foundation | Reproducible local environment and CI pipeline | 12 | 0 | 0% | 36.5 | 20 | -16.5 | 0 | -36.5
5 | 2026-09-14 | 2026-09-20 | Football data integration | One competition imports and refreshes reliably | 12 | 0 | 0% | 44 | 20 | -24 | 0 | -44
6 | 2026-09-21 | 2026-09-27 | Football information pages | Competition, team, player and fixture pages usable | 11 | 0 | 0% | 40 | 20 | -20 | 0 | -40
7 | 2026-09-28 | 2026-10-04 | Live match centre | All core match states and live updates demonstrated | 11 | 0 | 0% | 39 | 20 | -19 | 0 | -39
8 | 2026-10-05 | 2026-10-11 | Authentication and personalisation | Secure accounts, follows and preferences working | 12 | 0 | 0% | 45.5 | 20 | -25.5 | 0 | -45.5
9 | 2026-10-12 | 2026-10-18 | Community platform | Feeds and match discussions working safely | 12 | 0 | 0% | 48 | 20 | -28 | 0 | -48
10 | 2026-10-19 | 2026-10-25 | Moderation and safety | Reports, enforcement, audit and appeals demonstrated | 14 | 0 | 0% | 58 | 20 | -38 | 0 | -58
11 | 2026-10-26 | 2026-11-01 | ML dataset and baseline | Leakage-safe baseline evaluated chronologically | 12 | 0 | 0% | 40 | 20 | -20 | 0 | -40
12 | 2026-11-02 | 2026-11-08 | Improved ML and integration | Explainable prediction appears on match page | 12 | 0 | 0% | 46 | 20 | -26 | 0 | -46
13 | 2026-11-09 | 2026-11-15 | Notifications and official links | Deduplicated alerts and verified outbound links working | 13 | 0 | 0% | 51 | 20 | -31 | 0 | -51
14 | 2026-11-16 | 2026-11-22 | Integration and optimisation | Accessible, responsive release candidate | 12 | 0 | 0% | 52 | 20 | -32 | 0 | -52
15 | 2026-11-23 | 2026-11-29 | Security and release testing | No critical security or P0 journey failures | 14 | 0 | 0% | 61 | 20 | -41 | 0 | -61
16 | 2026-11-30 | 2026-12-06 | Deployment and portfolio packaging | Deployed demonstration and complete portfolio case study | 14 | 0 | 0% | 53 | 20 | -33 | 0 | -53

## Documentation
ULTRAS — DOCUMENTATION CHECKLIST
Track each product, design, engineering, safety, ML and portfolio document alongside the implementation.
Doc ID | Document | Purpose | Target Week | Due Date | Status | Reviewer | Last Updated | Evidence / Link | Notes
D01 | Project brief | Defines the problem, audience, scope and success criteria | 1 | 2026-08-23 | Not Started | Finlay
D02 | Product Requirements Document | Records testable P0 product requirements | 1 | 2026-08-23 | Not Started | Finlay
D03 | User stories and acceptance criteria | Maps user needs to testable behaviour | 1 | 2026-08-23 | Not Started | Finlay
D04 | Feature priority and out-of-scope register | Protects the MVP from uncontrolled expansion | 1 | 2026-08-23 | Not Started | Finlay
D05 | Football-data provider comparison | Supports provider and competition selection | 1 | 2026-08-23 | Not Started | Finlay
D06 | Competitor audit | Records useful patterns and differentiation | 1 | 2026-08-23 | Not Started | Finlay
D07 | Research summary and open questions | Separates evidence from unresolved assumptions | 1 | 2026-08-23 | Not Started | Finlay
D08 | Product risk register | Tracks product, technical, safety and delivery risk | 1 | 2026-08-23 | Not Started | Finlay
D09 | Sitemap | Defines page hierarchy and navigation | 2 | 2026-08-30 | Not Started | Finlay
D10 | Core user-flow diagrams | Documents critical user and moderator journeys | 2 | 2026-08-30 | Not Started | Finlay
D11 | Low-fidelity wireframes | Validates layout before visual polish | 2 | 2026-08-30 | Not Started | Finlay
D12 | High-fidelity core screens | Defines intended interface quality | 2 | 2026-08-30 | Not Started | Finlay
D13 | UI design system | Documents tokens, components and states | 2 | 2026-08-30 | Not Started | Finlay
D14 | Database ERD | Defines data entities and relationships | 3 | 2026-09-06 | Not Started | Finlay
D15 | Data dictionary | Defines fields, types, constraints and sources | 3 | 2026-09-06 | Not Started | Finlay
D16 | Data retention schedule | Defines lifecycle for personal and social data | 3 | 2026-09-06 | Not Started | Finlay
D17 | System architecture diagram | Shows application and data boundaries | 3 | 2026-09-06 | Not Started | Finlay
D18 | API specification | Defines contracts, permissions and errors | 3 | 2026-09-06 | Not Started | Finlay
D19 | Architecture Decision Records | Explains major technical choices | 3 | 2026-09-06 | Not Started | Finlay
D20 | Threat model | Identifies assets, abuse cases and controls | 3 | 2026-09-06 | Not Started | Finlay
D21 | Moderation workflow | Defines reports, cases, actions and appeals | 3 | 2026-09-06 | Not Started | Finlay
D22 | Testing strategy | Maps quality risks to test levels | 3 | 2026-09-06 | Not Started | Finlay
D23 | Community Guidelines | Explains permitted and prohibited behaviour | 10 | 2026-10-25 | Not Started | Finlay
D24 | Harmful-content taxonomy | Classifies safety risks consistently | 10 | 2026-10-25 | Not Started | Finlay
D25 | Moderation decision matrix | Supports consistent enforcement | 10 | 2026-10-25 | Not Started | Finlay
D26 | ML experiment specification | Defines target, features, split and metrics | 3 | 2026-09-06 | Not Started | Finlay
D27 | Dataset description | Documents provenance and transformation | 11 | 2026-11-01 | Not Started | Finlay
D28 | ML experiment log | Records reproducible experiments and outcomes | 11 | 2026-11-01 | Not Started | Finlay
D29 | Model card | Documents model use, performance and limitations | 12 | 2026-11-08 | Not Started | Finlay
D30 | ML evaluation report | Compares baselines and improved model | 16 | 2026-12-06 | Not Started | Finlay
D31 | Security checklist and incident plan | Supports secure release and response | 15 | 2026-11-29 | Not Started | Finlay
D32 | Deployment guide and runbook | Explains release, rollback and recovery | 15 | 2026-11-29 | Not Started | Finlay
D33 | Final README | Presents setup, architecture and evidence | 16 | 2026-12-06 | Not Started | Finlay
D34 | Test and security report | Summarises verification and residual risk | 16 | 2026-12-06 | Not Started | Finlay
D35 | Project retrospective | Records learning, trade-offs and future work | 16 | 2026-12-06 | Not Started | Finlay
D36 | Demonstration video | Shows the product story in two to three minutes | 16 | 2026-12-06 | Not Started | Finlay
D37 | CV and portfolio case study | Presents the project for applications | 16 | 2026-12-06 | Not Started | Finlay

## Research Log
ULTRAS — RESEARCH LOG
Record sources, findings and decisions. Keep factual evidence separate from assumptions and future questions.
Research ID | Stream | Question | Suggested Method | Target Week | Due Date | Status | Source URL | Finding | Decision / Impact | Reviewed On | Notes
R01 | Football data | Which provider best covers the selected competition, live latency, history, line-ups and player data? | Provider matrix and trial requests | 1 | 2026-08-23 | Not Started
R02 | Data licensing | What may be stored, displayed and used for ML or a public portfolio? | Provider terms and direct clarification | 1 | 2026-08-23 | Not Started
R03 | Initial competition | Which competition has the most complete affordable dataset? | Coverage comparison | 1 | 2026-08-23 | Not Started
R04 | Competitors | How do current products handle scores, feeds, discussions, alerts and safety? | Structured product audit | 1 | 2026-08-23 | Not Started
R05 | Supporter behaviour | How do users follow matches and which alerts are valuable rather than annoying? | Short interviews or questionnaire | 1 | 2026-08-23 | Not Started
R06 | Safety | Which football-specific harms need special controls during matchday traffic? | Risk review and official guidance | 1 | 2026-08-23 | Not Started
R07 | Privacy | What data is necessary and how long should social, account and moderation data be retained? | Retention assessment | 3 | 2026-09-06 | Not Started
R08 | Where to watch | Which official source can provide region-aware broadcast listings and deep links? | Source and licence comparison | 13 | 2026-11-15 | Not Started
R09 | Ticket links | How can official ticket links be validated without making availability claims? | Club and competition source review | 13 | 2026-11-15 | Not Started
R10 | Ticket exchange | Would authorised club partnerships make face-value resale legally and operationally viable? | Future feasibility study only | 16 | 2026-12-06 | Not Started
R11 | Authentication | Which implementation best fits secure sessions, verification and recovery? | Technical comparison and ADR | 3 | 2026-09-06 | Not Started
R12 | Live updates | Do polling, SSE or WebSockets best fit provider limits and portfolio scale? | Prototype and architecture decision | 3 | 2026-09-06 | Not Started
R13 | Notifications | Which channels and providers suit reminders, live alerts and delivery evidence? | Provider comparison and prototype | 8 | 2026-10-11 | Not Started
R14 | ML feasibility | Is there sufficient historical and time-stamped player/line-up data for a fair model? | Dataset audit | 3 | 2026-09-06 | Not Started
R15 | Official accounts | What evidence and permissions should be required to claim a team or player page? | Verification workflow research | 2 | 2026-08-30 | Not Started
R16 | Moderation operations | What staffing assumptions and escalation process would a public launch require? | Operational risk assessment | 10 | 2026-10-25 | Not Started

## Guide
ULTRAS — TRACKER GUIDE
A short operating guide for keeping the workbook useful throughout the build.
How to use the tracker
1 | Begin on Task Tracker | Filter by Week, Phase, Category, Priority or Status. Update only the editable tracking fields.
2 | Update progress honestly | Use Progress % for partial work and Status for workflow. Mark Complete only when completion criteria are satisfied.
3 | Record evidence | Add a commit, pull request, design file, screenshot, test report or document link in Evidence / Link.
4 | Log actual hours | Actual Hours helps you compare planned effort with reality and improve later estimates.
5 | Review every Sunday | Use Weekly Plan to record completed work, carried tasks, risks, decisions and the next three priorities.
6 | Keep research auditable | Research Log should contain source URLs, short findings and the product or technical decision produced.
7 | Update documentation continuously | Do not wait until Week 16. Mark documents Needs Update whenever implementation changes their assumptions.
8 | Protect the MVP | Defer P1/P2 work while a critical P0 task, test, security control or document remains incomplete.
Status definitions
Not Started | No material work has begun | 0%
In Progress | The task is actively being worked on | 1–89%
Blocked | A dependency or decision prevents progress | Record blocker in Notes
Ready for Review | Work is complete but needs checking | Usually 90–99%
Complete | Completion criteria and evidence are satisfied | 100%
Deferred | Intentionally removed from the active release | Explain scope decision
Recommended weekly rule: complete or consciously reschedule unfinished P0 work before pulling additional future features into the sprint.

## Dashboard Data
Status | Task Count | Phase | Progress | Week | Planned Hours | Actual Hours
Not Started | 205 | Discovery & Scope | 11.76% | 1 | 36 | 2
In Progress | 0 | UX & Product Design | 0% | 2 | 41.5 | 0
Blocked | 0 | Technical Design | 0% | 3 | 47.5 | 0
Ready for Review | 0 | Foundation & Data | 0% | 4 | 36.5 | 0
Complete | 2 | Football Core | 0% | 5 | 44 | 0
Deferred | 0 | Accounts & Community | 0% | 6 | 40 | 0
|  | ML & Notifications | 0% | 7 | 39 | 0
|  | Release & Portfolio | 0% | 8 | 45.5 | 0
|  |  |  | 9 | 48 | 0
|  |  |  | 10 | 58 | 0
|  |  |  | 11 | 40 | 0
|  |  |  | 12 | 46 | 0
|  |  |  | 13 | 51 | 0
|  |  |  | 14 | 52 | 0
|  |  |  | 15 | 61 | 0
|  |  |  | 16 | 53 | 0